## Slide 1: Project Update
“Lightning Round”
An update to the HSPC Community
2 August 2017

## Slide 2
Establishing a community consensus by target date of 2017
Baselined HSPC Transition Map Framework
Draft HSPC Roadmap Document Skeleton
Produce Alpha Draft of Roadmap Document
Baseline Roadmap Framework (July 2017)
Baseline content inclusion criteria (July 2017)
Produce initial draft (Alpha) of Roadmap document (August 1)
------------------------------------------------------------------
Produce Beta Release of Roadmap Document (September 30)
Produce 1.0 Version of Roadmap (December 31)
Effort was extended via broadening the skeleton document to allow for improved understanding beyond the transition map itself
A formal list of inclusion criteria was added to assure consistency in use of milestones included in Roadmap
Pressures
Scope Added
Dependencies
Milestones
Scope Removed
Artifacts Delivered
Concerns
HSPC Roadmap – Project Leads: (Ken Rubin, VHA; Jason Lee; Open Group)
To develop an industry Roadmap illustrating key activities and impacts of HSPC and the HSPC community as affecting the broader HIT landscape. This will establish a community-accepted vision, key milestones, and major deliverables.
HSPC Voting guidelines for formal acceptance of the document as a community artifact
No lead presently for Security Swimlane
Segment “breakout groups” have not yet realized an effective delivery cadence
Incorrect expectations that the scope is limited to SOA (it is actually all strategic HSPC work)
None
Listserv has been established: roadmap@hspconsortium.org
Wiki site has been revised and is live: http://roadmap.healthinterop.org
New and Noteworthy

## Slide 3
Controlling access to member-only services effectively requires an SSO system.
Establishing a realistic medium-term deliverable schedule
Disjoint expectations of HSP scope and existing uses of “platform” term.
Draft v0.6.0 marketplace specification.
HSP unification diagram draft.
Proposed identity management portion of HSP
Near complete patches for HSP-compliant builds of NIH LexEVS terminology service (CTS2) and HAPI-FHIR.
Segment consensus of unified reference platform architecture (September 30)
Core services established, inclusive of terminology service(s) and common SSO/IDP authority (November)
Public Marketplace GA with small selection of notable/useful services (March?)
Segment scope broadened to include both infrastructural and hosted software application-level services.
Availability of select non-F/OSS software services.
Sandbox support for “Knowledge Execution Engines” as part of future vision.
“CDS Hooks” at roadmap level.
Pressures
Scope Added
Dependencies
Milestones
Scope Removed
Artifacts Delivered
Concerns
HSPC Roadmap – Project Leads: (Preston Lee, VHA; Scott Narus, Intermountain)
To develop an industry Roadmap illustrating key activities and impacts of HSPC and the HSPC community as affecting the broader HIT landscape. This will establish a community-accepted vision, key milestones, and major deliverables.
Concrete business model and licensing decisions.
Establishing a common account directory for all platform services to authenticate against. “HSPC ID” SSO system
??? Assuming Ontoserver content will be managed by data track, but deployment and operation will become part of core infrastructure and be subject to the same access policies/processes as other core services
Lack of “doers” to work on community-owned technical deliverables.
Unifying existing “platform” concepts not in individual project self interests.
Vendor neutrality not a vendor interest.
CDS Connect not F/OSS (according to MITRE)
Google Group established: platform@hspconsortium.org
API specs normative in OpenAPI: https://www.openapis.org
New and Noteworthy
Technical services around community cloud
More complex low-level orchestration

## Slide 4
Establishing sustainability plan (supportive revenue)
Community outreach needs to expand, challenging due to limited resourcing
FHIR 3.0 Support
Terms of Use and Privacy Agreement
Specification and Reference Implementation of SMART App Registration
Social Login
Embedded App Simulator
HIT Developers Conference (March 2017)
FHIR 3.0 Support (May 2017)
Embedded App Simulator (June 2017)
CDS Hooks Collaboration Agreement (July 2017)
User base up 100% since march (386 -> 777)
------------------------------------------------------------------
CDS Hooks transition to HSPC Sandbox(August 2017)
CDS Hooks App Link (September 2017)
Argonaut Profile Support (October 2017)
Terminology Server Integration (November 2017)
CDS Hooks Collaboration
Pressures
Scope Added
Dependencies
Milestones
Scope Removed
Artifacts Delivered
Concerns
HSPC Developer Resources Initiative– Project Leads: (Scott Narus, Intermountain Healthcare, Rick Freeman, Interopion)
Provide development aids, validation tools, educational resources, and a collaboration space for innovators to ensure the HSPC open ecosystem maintains its neutrality while accelerating its adoption.
OntoServer Stand-up
Need to cross coordinate common infrastructure needed for other initiatives.
Long-term resource allocation in question
Production support is growing as user base grows, need more resources (~800 users)
None

## Slide 5: SOLOR Wound Assessment Susan Matney/Keith Campbell
Deliverables
Sample value set to CIMI for HL7 ballot
October 30th 2017 – Release of HSPC SOLOR Extension for Wound Assessment
Milestones
  Team is using JIRA and Confluence
  Value sets and reference sets are being created in termSpace
  Editorial guidelines documentation started
  Recurring coordination meetings between CIMI & SOLOR
Scope Change
None at this time
Dependencies
None at this time
Project Risks
Terminology alignment with CIMI Models
CIMI timeline for SNOMED CT Extension for Wound Assessment
  Project Description: To develop SNOMED CT SOLOR Extension to support CIMI Wound Assessment. The SOLOR Wound Assessment Extension contains new concepts and reference sets (value sets)
Important links:
HSPC SOLOR Confluence webpage
HSPC SOLOR JIRA webpage
termSpace SOLOR project