## Slide 1
HSPC Terminology and Information Model Initiative Update
Susan Matney, PhD, RNC-OB, FAAN (Initiative Co-lead)
Keith Campbell, MD, FACMI (Initiative Co-lead)
8/02/2017

## Slide 2: Terminology and Modeling Initiative:
Develop terminology and information models as a foundation for true semantic interoperability
  Based on real world, technical, high priority use cases brought to us by the member community.
Notes: Keith wants to “tweak” information models, CIMI and CEMs are “instance models” could be contextual models too.

## Slide 4: Deliverable 1: Develop the CIMI Content Architecture (overseen by HL7 CIMI WG)
Goal 1: Develop the high level reference archetypes (patterns) and ballot
    Assigned to : CIMI
  CIMI Model Style Guide in Sept ballot
  Archetypes included: Actor, Organization, Encounter, Evaluation Result, Procedure, Assertion, Medication, Device
Goal 2: Create and ballot the CIMI Reference and Foundational Archetypes
    Assigned to : Claude Nanjo/Joey Coyle
  Patterns above developed and in ballot
  Architecture guide in ballot
  Future patterns (Orders, Procedure specializations…)
Notes: DCM reuse will be a metric of success, could be around forms/templates/registries with the number completed and reuse
Tooling repository dependency (Model Repository Tool)

## Slide 5: Deliverable 2 Pilot Projects
  OPA/ACOG Family Practice Annual Report (FPAR)
    119 FHIR Profiles Created
    Working in Implementation Guide
    SMART on FHIR app final deliverable (contracting in process)
  Skin/Wound Assessment
    Using this project to develop SOLOR content and processes
    Reference sets developed in Termspace
    Jira project developed and tracking
  Starting Projects
    Vital Signs – common models compared and data set created
    Common labs – met with HL7 Orders & Observations
Notes: Need to articulate all these things and how they relate to each other
Simplify it

## Slide 6: Deliverable 3: Define Model Development Pipeline
Goal 1: Model Request Process Model Development
      Assigned to : Susan/Keith
  Process diagrammed (analysis, terminology and model mapping, content creation)
  Define Scope Templates
  Use Case Template Development
  Define Analysis Process
  Identify content curation process (SOLOR)
  Define and Document Model Development Process
Goal 2: Model Development Process
    Assigned to : Susan/Claude/Jay
  Identifying common principles and processes during SOLOR development – document started
  Model request spreadsheet being evaluated and refined

## Slide 7: Request to CIMI to FHIR
Data Collection
Content Review
Content Analysis
Mapping
Encoding and Content Request
Model Mapping
Model Creation
FHIR Creation

## Slide 8: Confluence/Jira
https://healthservices.atlassian.net/wiki/spaces/SOLOR

## Slide 9: Deliverable 4: SOLOR terminology editing environment (overseen by Keith Campbell)
Goal 1: Determine Terminology Editing Environment - done
    Assigned to : Keith Campbell
  Using termSpace and HSPC SNOMED CT extension namespace
  Content creation is based on projects
  Develop long term maintenance process (in progress)
Goal 2: Define process for SOLOR terminology development
    Assigned to :Keith/John Kilbourn
  Tasks defined in Jira
  Biweekly meeting with CIMI/SOLOR
Notes: Notes from John – needs to be further refined, concerns about resources

## Slide 10: Deliverable 4: Provide SOLOR terminology services (overseen by Keith Campbell)
Goal 3: Determine Terminology Services required for model binding
    Assigned to : CIMI Pattern Development Subgroup (Susan will lead)
Goal 4: Identify and implement terminology server
    Assigned to : Keith
  Contract signed for Ontoserver
  Populated with SNOMED and LOINC
Goal 5: Implement Terminology Services for model binding
    Overseen by : Keith
  Recently delegated to Cognitive
Notes: Notes from John – needs to be further refined, concerns about resources

## Slide 11: Deliverable 5: Define versioning and governance processes for terminology and models
Goal 1: Terminology Versioning and Governance Processes
    Assigned to: Keith Campbell
  STAMP
    Status, Time, Author, Module, Path
Goal 2: Model Versioning and Governance Processes
    Assigned to: Claude/Jay/Stan
Notes: Move to knowledge content initiative

## Slide 12: Questions