## Slide 1: Lightning Round
July 2018

## Slide 2: Initiative: SOA Reference Implementation

## Slide 3: SOA Reference Architecture and Implementation Initiative
None at this time
Worksession planned for September summit
Uncoordinated membership interest
More effective collaboration with contributing entities is required
None
Milestones Achieved
Upcoming Milestones
Artifacts Delivered
Risks
Models implemented by Cognitive, HarmonIQ, Providence, Mayo/ASU. Intermountain and VA
HIMSS Demo with Cognitive 2016
HIMSS Demo with DXC 2017
Marketplace demo (Preston Lee)
Production implementations im BPM/DMM/at Intermountain (Peter Haug), HanronIQ/LSUdemo with DXC (Bo Dagnall) (Rob Reynolds/Bryn Rhodes)
Knowledge authoring in CQL (Bryn Rhodes)
Work by Cognitive in Drools
Work on continous deivery and microservoces (Rob Reynolds)
Scope Added
Scope Removed
Perspecta has indicated interest in contributing a conceptual architecture
Providence work on
VA and several industry efforts to mature a reference architecture (HL7, OSEHRA, OMG, Open Group)
New and Noteworthy
Project Summary: To converge industry around a shared reference architecture to be used as a basis to foster compliant implementations and thus interoperable health platforms
Need to converge all efforts to help with industry convergence
Early Adopter Contributors need to be coordinated
Identify a partnering community with which to collaborate
Concerns
None
Opportunities

## Slide 4: Initiative: Terminology and Modeling

## Slide 5: Terminology and Modeling
None at this time
RF2 Export – July 2018
Vital Signs/Suicide Content – Sept 2018
Need development resources
Need technical writer
Milestones Achieved
Upcoming Milestones
Artifacts Delivered
Risks
FedHealth Architecture Learning Series 2
May 2018 v1.2 SOLOR Viewer
Assemblages of Content Improvements
Content Improvements RF2 files
Skin/Wound Assessment Extension RF2 files
Scope Added
Scope Removed
Dependencies
FedHealth IT Innovation Award
OSEHRA Lifetime Achievement Award Keith Campbell
New and Noteworthy
Project Summary: SOLOR
Concerns
Funding
Exploring integration of genomics to compliment phenomics in SOLOR

## Slide 6: Terminology and Modeling Initiative: Skin/Wound Assessment
Define next release
Observable entity SNOMED Codes for all LOINC observations
Simple LOINC map refset
Skin/Wound Assessment SOLOR Extension v.1 Release Files – November 14th (24 refsets created)
Ongoing collaboration with wound SMEs is limited
6 additional attributes from Tissue analytics
Milestones Achieved
Upcoming Milestones
Artifacts Delivered
HSPC registration process for terminology licenses
Risks
Scope Added
Scope Removed
Dependencies
SNOMED/NLM indicated they wanted content submitted that has been tested, integrated into a coherent model w/ supporting content
New and Noteworthy
Project Summary: To develop content (SOLOR/LOINC) to support CIMI Skin/Wound Assessment.
Model still being updated during CIMI modeling demonstration project
Concerns
All refsets created as Value Sets in the Value Set Authority Center (VSAC)
New LOINC codes received
LOINC Panel updated

## Slide 7: Terminology and Modeling Initiative: Vital Signs
Create/Update Vital sign terminology and mappings in SOLOR
Finalize CEMs with terminology bindings and translate CEM to CIMI archetypes
Publish Archetypes and build FHIR Profiles
Update Style Guide documentation
Body location value set should contain only arteries. Many intuitions use extremities instead
Observable entities for observations
Milestones Achieved and Artifacts delivered
Upcoming Milestones
Risks
Scope Added
Scope Removed
Dependencies
Project Summary: Develop CIMI logical models bound to standard terminologies for FHIR vital sign profile qualifying attributes.
Up-take is a risk because the resulting FHIR profile will be profiled off of the current vital sign profile
Concerns
Creating all value set identifiers and SNOMED CT content in SOLOR for:
  Observable entities for observations
  Value sets for all qualifying vital signs attributes mentioned in the FHIR profile

## Slide 8: Terminology and Modeling Initiative: Family Practice [FPAR 2.0]
IG development complete
Collaboration with SMART on FHIR team
FPAR 2.0 FHIR profiles delivered
Crosswalk document delivered
Lack of maturity in tooling and automated processes
Unable to retrieve value sets from VSAC
Supporting validation testing of FHIR profiles.
Milestones Achieved
Upcoming Milestones
Artifacts Delivered
Dependency on FHIR publish tool to publish HSPC FHIR profiles
Risks
Scope Added
Scope Removed
Dependencies
An HSPC Implementation of FPAR 2.0 resources to help validate the profiles
IG follows the model of CCDA and Genomics FHIR groups.
Intermountain tools can now automate FHIR profile generation from CEML.
New and Noteworthy
Project Summary: This project is a pilot of the Office of Population Affairs (OPA) family practice annual reporting (FPAR) process in collaboration with American College of Obstetricians and Gynecologists (ACOG).
Issues in ‘FHIR Publishing tool’ keeping us from publishing FPAR Profiles to HL7 FHIR.
Concerns
Phase 1 0 CIMI Models and FHIR Profiles Complete
Working on Implementation Guide
FHIR Profiles in testing

## Slide 9: Initiative: Development Platform/FHIR Sandbox

## Slide 10: Development Platform/FHIR Sandbox
None at this time
Sandbox Manager v3 rollout
CQF support
DaVinci / FPAR profiles support
Limited resources
Milestones Achieved
Upcoming Milestones
Artifacts Delivered
Risks
Sandbox Manger v3-beta
HL7 Connectathons
HIMSS Interoperability Showcase
FHIR Dev Days
Scope Added
Scope Removed
Dependencies
EOL HSPC 1-4
1500+ HSPC Developer accounts
New and Noteworthy
Project Summary: Provide development aids, validation tools, educational resources, and a collaboration space for innovators to ensure the HSPC open ecosystem maintains neutrality while accelerating its adoption.
Meeting growing user expectations (system availability and support)
Introducing subscription model
Limited community outreach
FPAR modeling team
CQF group
HAPI, MitreID Connect
Concerns
Sandbox Manager v3-beta (React)
EHR Simulator
Improvements to HSPC sandbox (systems monitoring, status updates page, security, DB, internal models, HAPI 3.3 / FHIR R4, AWS Optimization, FireBase API Integration, Pipelines integration, blog, terms and conditions, instance profile validation, news feed, gallery improvements, dev site updates, Pub Sub integration, etc)

## Slide 11: Initiative: Tooling

## Slide 12: Tooling Initiative
None at this time
Finalize Tooling Roadmap
Tool development without requirements
Potentially shifting standards
None
None
Milestones Achieved
Upcoming Milestones
Artifacts Delivered
Risks
Requirements Gathering
Draft – Tooling Roadmap
Tool swim lane contributed to the HSPC Clinical Modeling Process
Scope Added
Scope Removed
Dependencies
New and Noteworthy
Project Summary: Addressing the tooling ecosystem to support HSPC activities
Breadth and depth of the needs
Clear and consistent direction in the modeling process
Concerns

## Slide 13: Initiative: Support Conformance and Certification Testing

## Slide 14: Support Conformance and Certification Testing Initiative
None at this time
Form the working group with regular calls
Requirements defined
Determine the conformance criteria
Testing plan development
Adequate expertise engaged
Clear business objectives
Milestones Achieved
Upcoming Milestones
Artifacts Delivered
Adequate participation
Risks
Scope Added
Scope Removed
Dependencies
New and Noteworthy
Project Summary: Setting HSPC Conformance Criteria
Complex topic
Concerns

## Slide 15: Break

## Slide 16: Initiative: Support a Vendor and Provider Neutral Marketplace

## Slide 17: HSPC Marketplace
None at this time
Architecture Review Board review
Informative ballot
z
Speed of formal SDO processes
Informative balloting
Milestones Achieved
Upcoming Milestones
Artifacts Delivered
HL7
Risks
Submitted project materials to HL7 architectural review board.
Project scope statement
Risk mitigation analysis
Scope Added
Scope Removed
Dependencies
New and Noteworthy
Project Summary: Vendor and Provider Neutral Marketplace
External processes, reviews, and approvals.
Concerns

## Slide 18: Initiative: Sharing Knowledge Content

## Slide 19: Sharing Knowledge Content Initiative
None at this time
Revision/Extension of BPM Field Guide.
Review-HSPC Roadmap.
ePulmonary Embolism-Phase 3
Support of AHRQ CDS Connect governance/tools
Resources for Wide Range of Knowledge Modeling/Piloting initiatives.
Management of new and existing projects.
Future of HL7 KNART spec
CDS Connect
Milestones Achieved
Upcoming Milestones
Artifacts Delivered
Risks
BPM Field Guide, version 1 Released.
Continued Maturation of BPM-based Pregnancy Use Case.
Availability of BPM Authoring Tools for HSPC Members.
15 months of KNART Content Development
Scope Added
Scope Removed
Dependencies
Rapid Evolution of HL7 CDS Hooks Standard.
Version 1.2 Decision Modeling Notation
New Versions of CMMD and BPMN.
New and Noteworthy
Project Summary: Ongoing Analysis and Adaptation of OMG/HL7 Business Knowledge Content Management Standards for Medicine.
Choices between FHIR-DSTU 2 and FHIR-STU 3/4.
Availability of needed CIMI/FHIR models for Information Artifacts
  Complex artifacts for Alert Event, etc.
Loss of KNART Development Momentum
CIMI/FHIR Models for data Reads/Writes, Orders, Decisions, Etc.
HSPC Sandbox models for Security.
Clinical SMEs; VHA
Concerns
Final Version 1 of Field Guide Released.
BPM Pregnancy Use Case Continued Maturation.
BPM Milestones added to HSPC Roadmap (Released and Available).
Maturation of BPMN Use Case using HSPC Sandbox/FHIR (ePulmonary Embolism-phase 2)
92 Individual KNARTs
12 “Composite” Integrations
A Draft Composite Schema

## Slide 20: Roadmap

## Slide 21: Roadmap
None at this time
Sept 2018: Commence revisions for 2019 Roadmap
December 2018: Roadmap Vote (Membership)
HSPC still determining how best to use Roadmap in operation
Milestones Achieved
Upcoming Milestones
Artifacts Delivered
Risks
Roadmap was adopted and published Q1 2018
June 2018: Roadmap Detail/Quality Review conducted
Scope Added
Scope Removed
Dependencies
Revisit of Roadmap in light of CIIC objectives
New and Noteworthy
Project Summary: The HSPC Roadmap documents a strategic vision for the organization, organized into segments and swimlanes, detailing key milestones and deliverables objectives for the community.
Ineffective use of artifact. Roadmap not driving HSPC strategy to its potential
Updates re: HSPC/CIIC union subject to Board guidance
Concerns
CIIC objectives, drivers, products (TBD)
None

## Slide 22: Member Projects

## Slide 23: Questions

## Slide 24: CIIC: Projects

## Slide 25: CIIC Projects Work Group
None at this time
Define and implement project approval process
Launch projects
Establish project pipeline
Clarifying roles in the merged organization
N/AN/A
N/A
Milestones Achieved
Upcoming Milestones
Artifacts Delivered
Risks
Project intake form published online
Submissions from six projects to date (invited)
Documented the presence of 25 CIIC-related projects
Project intake form for project evaluation
CIIC list of commitments
Candidate project descriptions
Scope Added
Scope Removed
Dependencies
Now accepting project description submissions
Seeking CDE process documentation experience
New and Noteworthy
Project Summary: The Projects Work Group focuses on the coordination and advancement of CIIC projects through information sharing, clinical and technical feedback, documentation of a successful CDE process, and resourcing as appropriate.
Lack of availability of resources to support projects
Ability to coordinate content across projects
Establishing Clinical Steering Committee
Tooling for pipeline, CDE creation
Concerns

## Slide 26: CIIC: Marketing

## Slide 27: CIIC: Marketing
None at this time
Working on a contact database of potential interested contacts and previous attendees
Created an elevator speech explaining CIIC
Unified Message
Coordination with other communities
Merger with HSPC
Milestones Achieved
Upcoming Milestones
Artifacts Delivered
Risks
Working group regularly meeting every two weeks.
Scope Added
Scope Removed
Dependencies
Engagement of Weber Shandwick working on the combined messaging of CIIC and HSPC
Working on a new name for the combined organization
New and Noteworthy
Project Summary: Increase the visibility of CIIC and HSPC activities and engage new participants.
Resourcing
Confusion with other interoperability initiatives
Outside resources needed to accomplish goals.
Concerns

## Slide 28: CIIC: Technical

## Slide 29: CIIC: Technical
None at this time
Establish requirements
Review existing repositories
Plan for designing, building/leveraging, testing operations
Resources
Funding
Other technical activities- process of model intake, etc.
Milestones Achieved
Upcoming Milestones
Artifacts Delivered
Risks
Identified technical group as model repository group
Identified team
Scope Added
Scope Removed
Dependencies
TEAM Established
Stan Huff
Patrick Langford
Craig Parker
Joey Coyle
Rick Freeman
Steve Bratt
Scott Narus
Claude Nanjo
Richard Esmond
Galen Mulrooney
Susan Matney
Laura Heerman- Langford
Virginia Riehl
Rebecca Baker
New and Noteworthy
Project Summary: Plan/establish a model repository
Pace of repository build vs pace of need
Resources
Funding
Models for repository
Clinical organizations guidance on models/approval of preferred model
Terminology services- working real time w terminology server
Concerns
Initial/preliminary charter
Scope for RG: concept, use cases, requirements, sharing info on existing systems, governance
Notes: Requirements- storage, search, comparison, dependencies, maturity, versioning, etc.
Initial scope for the RG
  Concept.
  Use cases.
  Requirements. (e.g., storage, search, comparison, dependencies, maturity, versioning…)
  Sharing info on existing systems that could be leveraged.
  Plan for designing, building/leveraging, testing, operations.
  Think ahead about the technology needed to support governance of the repository – It’s likely that the governance requirements would be decided elsewhere. However, tech considerations would need to be inputs to the decision.
Group should come up with an initial draft as soon as possible. Input from the clinical societies and other users (industry, etc.) would be important before the plan is finalized and executed.

## Slide 30: Project: Perspecta “HealthConcourse”

## Slide 31: “HealthConcourse” Digital Health Platform [SOA, Sandbox, etc.]
None at this time
Sandbox
Continued alignment with industry bodies, standards, partners
Milestones Achieved
Upcoming Milestones
Artifacts Delivered
Risks
“HealthConcourse” Digital Health Platform [SOA, Sandbox, etc.]
FHIR-Based Reference Architecture, Implementation
Terminology Service
Security Labels & Tags
CDS Hooks
Synthea
Reference Architecture (Sandbox Implementation?)
Open Source (VistA-FHIR Ingestion Tool)
Scope Added
Scope Removed
Dependencies
OSEHRA Innovation Award [Bo]
Data Lake, NLP, Blockchain for consent, Machine Learning, CDA-to-FHIR, API Manager, SecureIO
New and Noteworthy
Project Summary: ”HealthConcourse” Provides a Reference Architecture and Implementation for an Open Standards-Based Interoperable Ecosystem
Complacency vs Art-of-the-Possible
Time
Clinical input & use cases
Concerns